## DD CL rev.2
Vessel Name:
Vessel Type:
IMO Number:
Class (including Notations):
Repair (Build) yard:
Repair commencement (Steel cutting) date:
Delivery date:
| yard | PDT: prior dock trials | Class
| crew rank | DDT: during dock trials | Fleet Superintendent
| class | DST: during sea trials | Master
| workshop | PS: prior sailing | Chief Engineer
items mark with * are new items from the first edition | [7 empty] | (Equip) Fleet info reliability (non reliable: 1, most:0) | (Equip) makers / 3rd party info (non reliable: 1, most:0) | (Equip/ Proc) Probality Rating (frequent:5, probable:4, occational:3, remote:2, impropable:1) | L | failure consequence (Safety:3, pollution:2, commercial:1) | S | (Equip) back-up unit (1:No 0:Yes) | (Equip) alternate operating procedure (No:2, reduced perf:1, fully:0) | (equip/proc) interval (5/2.5Y:3, 1Y:2, 6/3M:1, 1M:0) | (Equip/proc) Type of inspection (visual:3, testing:2, minor overhaul:1, major overhaul:0) | (Equip) Idling machinery (Rarely:3, Occasional:2, continuous:1, Reciprocal:0) | (Equip) Expected spare parts delivery (route/makers) (>6m:3, >3m:2, >1m:1, <1m:0) | (Proc) alternative procedural controls (No verification:3,Crew verification:2,Yard verification:1,Class verification:0 | P | Final rating | Criticality / risk severity
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
1 | General Information
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
2 | Certification and Documentation | [6 empty] | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 0 | 6 | 8
2.1 | New Certificates / Test Records / Receipts issued during DD period verified to be onboard. | 2 |  | PDT |  |  |  | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 2 | 8 | 10
2.2 | Confirm Certificates / Endorsements are correct (forward copies to office ASAP). | 2 |  | PDT |  |  |  | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 0 | 6 | 8
2.3 | VGP requirements have been complied with / documentation in order. Separate Class Statement of Fact to include antifouling paint, chain locker cleaning, environmentally acceptable lubricants (stern tube, bow thruster, deck equipment) and any other VGP items. | 2 |  | PDT |  |  |  | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 0 | 6 | 8
2.4 | Class 'Factual Statement' that the Special Survey has been completed and that the ESP (Executive Hull Summary & Thickness Measurements) documentation is under preparation by Class head office and will be issued in due course. | 2 |  | PDT |  |  |  | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 0 | 6 | 8
2.5* | Class factual statement for the pressure test of piping conducted. | 2, 8.3 |  | PDT |  |  |  | - | - | 2 | 2 | 1 | 1 | - | - | 3 | 3 | - | - | 0 | 6 | 8
2.6* | Class factual statement for the ETA structural support members. | 2, 9.28 |  | PDT |  |  |  | - | - | 2 | 2 | 3 | 3 | - | - | 3 | 3 | - | - | 2 | 8 | 30
2.7 | All vessel drawings, Fire/ Safety/ Emergency plans are placed on-board. Special tools, and other ship property returned on board. | 2 |  | PS |  |  |  | - | - | 2 | 2 | 3 | 3 | - | - | 3 | 3 | - | - | 2 | 8 | 30
2.8* | QMS procedures for the Drydock have been properly evidenced and records filed, inclusive of Risk assessment, Safety Committee Meeting records and Management of Change records | 2, 5.7 |  | PS | [5 empty] | 2 | 2 |  | 0 | [7 empty] | 0
2.9 | Upper deck – accommodation and out-fittings check for damages by shipyard. | 2.15 & 2.16 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
2.1 | Inspected tanks / void spaces / chain lockers – no person left inside verified.Tank vents and sounding pipes are free and clear of rags, bags and other means of restriction. | 2.9 |  | PDT |  |  |  | - | - | 2 | 2 | 3 | 3 | [7 empty] | 0
2.11 | Cargo-Ballast-Void spaces check for cleanliness /Water-tightness./ foreign objects after repairs and inspections. | 2.9 & 8.18 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
2.12 | M/E L.O. sump tank manhole gaskets inside cofferdam inspected for oil leakage. | 2.9 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
2.13 | Confirmation that all tanks and voids are free and clear of debris. | 2.9 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
2.14 | Agent has been informed for undocking time and port clearance has been obtained. | 2 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
3 | Crew Management | [9 empty] | 0 |  | 0 | [7 empty] | 0
3.1 | All ship personnel are adequately rested before departure. | 3.2 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
[11 empty] | 0 |  | 0 | [7 empty] | 0
3.2 | Muster and headcount, all crew on board prior to departure. | 3.1 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
[11 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
4 | Navigation and Communications | [9 empty] | 0 |  | 0 | [7 empty] | 0
4.1 | ‘Preparation for departure’ tests and checks prior departure. | 4.3, 4.7 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.2 | Navigation / Communication/intercom equipment (inclusive of emergency devices) / instruments operation test (Radars/ ARPA, Gyro Compasses, ECDIS, Steering gear/ Auto pilot, GMDSS/ Batteries, EPIRB/ SARTs) | 4.7 |  | PDT, DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.3 | Dead man alarm system, Navigation Bridge alarm system tested / activated. | 4.7 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.4 | Echo sounder and Doppler transducers functioning correctly. | 4.7 |  | DDT, DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.5 | All navigational equipment tested. | 4.7 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.6 | Temporary notices, Navtex, weather information received and passage plan prepared. ECDIS pre-departure check list “Bridge-24” completed. | 4.13, 4.20, 4.17 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.7 | Charts and publications, latest NTMS available onboard and ready to use for voyage. | 4.12 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.8 | Navigational, security plan, Suez Canal search lights, tested during dock trials. | 4.20, 7.4 |  | DDT
4.9 | Testing of general alarm, ship's whistles, and gongs. | 4.7, 4.8 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.1 | Emergency power supply (batteries, UPS & chargers. | 4.23, 10.36 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
4.11 | Magnetic compass to be adjusted. | 4.7 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
5 | Safety Management | [9 empty] | 0 |  | 0 | [7 empty] | 0
5.1 | Accommodation Ladders P & S and gangway operation/ load test. Class statement/ certificate issued. | 5.47 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.2 | L/boats P & S launching-hoisting operation test (incl. confirmation of correct MGO filling and air cylinder charge). Consideration should be taken for vessel’s charging cylinder and trading in cooler climates. Decreased air temperatures will reduce bottle pressures. | 5.27, 5.28, 5.29 & 5.30 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.3* | Check proper stowage of liferafts and auto release device/lashing. Portable equipment re-stowing verification | 5.28 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.4 | L/saving equipment in place (L/rings-EEBDs-ELSA etc.) and ready for use. | 5.44 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.5 | P/Room rescue winch in place or adequately available? | 5.2 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.6 | Firefighting equipment-accessories re-stowed in place-boxes etc. | 5.42 & 5.37 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.7 | MOB units checked in place. | 5.31 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.8 | CO2 system connected and ready for use. | 5.4 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.9 | Fire / Emergency Pumps operation test. (priming device and suction/discharge valves – check operating instructions properly posted). Pressure test fire main pipes / valves. | 5.38, 5.41 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.1 | Fire-Gas-Smoke-Thermal Detection alarms and General Alarm operation test. | 5.39 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.11* | Remote shut-off system for accommodation and engine room Fire doors / Flaps / Dampers operationally tested. | 5.45 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.12 | Pump room / accommodation / bosun’s store room gas monitoring systems tested. | 5.21 & 5.22 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.13 | Permanent fire extinguishing systems for E/RP/R Deck, Galley and Accommodation ready to use | 5.4 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.14 | Personnel Protective Equipment (PPE) available for use. | 5.5 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.15 | Gas monitoring system. | 5.21, 5.22 & 8.46 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.16 | All drills as per Regulations executed prior to sailing. | 5.12 & 5.13 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
[11 empty] | 0 |  | 0 | [7 empty] | 0
5.17 | Confirm that all measurements taken I calibration certificates received in order(as applicable) | 5.23 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.18 | All shipyard equipment has been removed and delivered prior to departure. | 5, 11.3 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.19 | Confirm that all shipyard personnel have disembarked. | 5, 7.3 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.2 | All sprinkler or fire suppression systems should be air tested to confirm free and clear, with no blanks in place (Pump Room, Fuel Oil Purifier Room, CO2 systems, Inert Gas systems, etc). | 5.4 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
5.21 | Pump Room safety systems tested and operational? Ventilation, Bilge Alarms, Atmospheric Monitoring, Communication Devices, etc. | 5.19 & 5.35 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
6 | Pollution Prevention | [9 empty] | 0 |  | 0 | [7 empty] | 0
6.1 | Garbage (oily liquids) rags delivery receipts supplied to Master (all slops sent ashore). | 6.2 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.2 | O/fill alarms, Shutdowns, and other steering alarms – E/Room, P/Room, Steering gear, Bosun's store space bilge alarms operation test operational / watertight and correctly set. | 6.11 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.3 | O.D.M system spectacle flange i.w.o S.W overboard valve to be turned/at closed position. ODME is simulation tested and calibrated – check operation of valves and recording function. | 6.4 & 6.13 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.4 | Main Cool. S.W. & Fire P/ps Emergency Bilge Suction closed. Seal no's (if applicable) recorded to engine log book. | 6.15 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.5 | Oily Water Separator overboard valve closed. Seal no. (if applicable) recorded in Oil Record Book. Oily water separator is simulation tested and calibrated. | 6.17 & 6.18 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.6 | Confirm that systems / piping have been flushed, as applicable and all bunker pipelines, manifolds, drains, vents and gauguging systems fully secured. | 6.4 & 6.8 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.7 | Contingency plan in case of failure: Emergency Plan & Training Manual – Pollution | 6.1 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
6.8 | Means of managing spills are in place such as continuous coaming, scupper plugs, and spills kits. | 6.2 & 6.3 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
7 | Maritime Security | [9 empty] | 0 |  | 0 | [7 empty] | 0
7.1 | Security inspection carried-out and entry made in bridge logbook. | 7.3 to 7.13 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
7.2* | Cyber Security awareness/ policy implemented onboard. Measures to prevent any breach in place. | 7.14 to 7.17 |  | PS
7.3* | All I/T & O/T systems secured after updates | 7.15 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
8 | Cargo and Ballast Systems - Petroleum | [9 empty] | 0 |  | 0 | [7 empty] | 0
8.1 | Confirm tightness no hydraulic leaks from valves / joints. | 8.3 & 8.62 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.2 | MMC vapour locks check for damages / gas tightness. | 8.12 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.3 | COW machines manual operation test-check for damages. | 8.34 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.4 | Heating coils pressure test-check for leaks-damages. | 8.15 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.5 | Hydraulic system activation-valves operation test i.w.o Deck-P/R-COT- WBT. Test all cargo valves and assess opening/shutting times. | 8.11 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.6 | P/V valves manual operation test. P/V breaker level to be checked (as/ if applicable). | 8.21 & 8.28 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.7 | C.O.Ps-W.B. Pumps, AUS (as far as practicable) operation test-lines/valves-joints pressure check for leaks. Including automation and emergency trip. Cargo/ ballast hatch covers structurally intact and water tight. | 8.8 & 8.10 |  | PDT. DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.8 | IG / N2 system activation-performance/alarms & trips test. | 8.22 to 8.26 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.9 | COTs-WBTs level/ pressure gauges performance-accuracy check-indicators in CCR. | 8.19, 8.24, 8.25, 8.26 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.10* | Check operation of deck seal unit and supply pump including water supply/level safety devices | 8.27 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.11* | Calibrate and check operation of Oxygen analysers and O2 content recording function | 8.26 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.12 | IG inlet branch – Mast Riser – main valves(inclusive of boiler uptake valves) operation test-check security pins-sockets. | 8.2 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.13 | Check individual lG / N2 remote tanks pressure indicators. | 8.13 & 8.19 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.14 | P/V valve leakage test. | 8.21 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.15 | IGS failure. | 8.22 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.16 | Gas monitoring system (if vacuum system utilised ensure tubing is free and clear of obstructions). | 8.46 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.17 | Manifolds are blanked, fully bolted and manifold valves and drains closed after pressure testing. | 8.3 & 8.41 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.18 | Mast riser leakages. | 8.19 |  | DST
8.19* | Cargo tanks High-level and overfill alarms tested and in good order. | 8.14 |  | DST
8.2* | Pumproom spaces are clean and all pumps, pipelines & valves are secured and instrumentation checked. | 8.44, 8.46 & 8.47 |  | PDT DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
8.21 | Operational trial of the thrusters if available. (Where DP equipment available) | 8.89 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
9 | Mooring | [9 empty] | 0 |  | 0 | [7 empty] | 0
9.1 | Mooring machinery / windlasses – all cranes operation tested. Hydraulic machinery check. | 9.14, 9.20 & 8.50 |  | PDT
9.2 | Mooring / anchoring inspection. | 9.14 to 9.23 & 8.50 |  | DST
9.3 | Anchor brakes are tightened and stoppers in position. | 9.15 |  | DDT
9.4* | Changes to Mooring Equipment is reflected within the ship's MSMP/LMP | 9.2 & 9.3 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
10 | Engine and Steering Compartments | [9 empty] | 0 |  | 0 | [7 empty] | 0
10.1 | Engine Room alarm / monitoring and extension system tested. | 10.2, 10.4 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.2 | Communication/radio facilities at Nav. Bridge wings, Upper deck fwd & aft, Steering gear, E.CR & C.CR tested. | 10.41 |  | PDT & DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.3* | Scrubber unit operation test, including scrubber pump and water supply safety interlock. | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.4* | Incinerator including safety devices to be tested. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.5* | Engine room valves remote shut-off and machinery shut-down system tested and working satisfactory. | 10.17 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.6 | Engine Room Departure' ECR-07 tests and checks prior departure. | 10.32 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.7 | Overhauled sea chests and valves are operational / watertight and correctly set. MGPS system operational check. | 10.31 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.8 | Main switchboard and emergency switchboard automation test (incl. cleaning and bus bar securing bolt test). | 10.23 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.9 | Operational test, alarm & all trips of all generator engines carried out. | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.1 | Emergency generator operational test (using all available means), alarm & trips (incl. Confirmation of MGO filling). | 10.16 & 10.34 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
[11 empty] | 0 |  | 0 | [7 empty] | 0
10.11 | Testing of M/E turning gear interlock function. | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.12 | Main Engine alarm, and trip system check carried out. Test by simulation ME safety alarms and slow/shutdown functions and settings. Check integrity and operation of oil mist detector unit | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.13* | Check ME crankcase and scavenging spaces and verify condition of bearings and pistons - measurements are to be taken as per PMS requirements – Blowers are to be run tested. | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.14* | Test proper operation of ME emergency and remote control stations and transfer control function | 10.33 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.15* | Check ME T/C oil level, prime pumps (as applicable) and test safety / alarm settings | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.16 | Aux. boiler(s) operational test, alarm & trips carried out. safety devices and relief valves are tested and calibrated. Test operation of feed / circulation pumps and auto-change/stand-by function | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.17* | Ensure gas boiler is internally inspected and pressure tested by pumps and safety relief valves tested and calibrated | 10.32 |  | DDT, DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.18 | Rudder all mode including emergency steering system operation test. | 10.16 and 10.39 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.19* | Test operation of No.1 and 2 steering gear power and control systems including auto change-over and failure alarms – check time for turning rudder from PS to STBD as per SOLAS requirement - check hydraulic oil header tanks levels and level alarms - check rudder carrier lubrication. Check rudder angle indicator, gyro repeater, emergency steering instructions and emergency communication with bridge. | 10.39, 10.40 and 10.41 |  | DDT, DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.2 | Main Engine manoeuvring system operational test from all stations carried out during sea trials. | 10.33 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.21 | Aux. machinery auto change over procedure tested during sea trials or dock trials, as appropriate. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.22 | Operational test of overhauled pumps during sea trials. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.23 | Operational trial of the Stern Tube System. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.24 | Air conditioning units tested and fresh air intake suction filters renewed. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.25 | Operational test of all miscellaneous systems that overhauled during D/D. Special attention paid to renewed / repaired items. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.26 | ICCP system operation and indication check. System to remain shut off for fifteen (15) days after undocking. At the due date, to be switched on again. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.27 | All emergency lights in E/R, P/R, deck and accommodation space tested / activated. | 10.15 & 11.9 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.28 | Main engine bypass LO filter, which must be used during dock trials, inspected – cleaned. | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.29 | All sea valves inspected for leakage. | 10.31 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.3 | Testing of all machinery space bilge alarms. | 10.30 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.31 | Machinery spaces have been adequately inspected to ensure no scaffolding or debris is left adrift. Further, all materials are properly secured for sea. | 10.15 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.32 | Steam to HFO tanks is opened and temperatures are normal. | 10.32 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.33* | Check service / settling tanks are free of excess sediments and level / temperature gauges in good condition | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Check level and level alarms of expansion tanks | [9 empty] | 0 |  | 0 | [7 empty] | 0
10.34* | Test operation of fuel oil system including supply/booster pumps, filtering arrangements and purifiers | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.35* | Test operation of ME lub-oil system including pumps, filtering arrangements and purifiers | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.36* | Test run FW cooling system and ensure proper de-aeration | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.37* | Test run SW cooling system and check efficiency | 10.32 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.38 | Main starting air receivers are both full (typically up to 28-30 bar). Check control air supply/reduction unit operation and delivery pressure | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.39 | Stern tube seals gravity tanks fwd and aft have been connected. | 10.32 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.4 | Stern tube has been confirmed full with lubrication oil, gravity tank observed at proper level. | 10.32 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.41 | Stern tube cooling water tank has been confirmed full. | 10.32 |  | PS | [6 empty] | 0 |  | 0 | [7 empty] | 0
10.42 | Intermediate shaft bearing oil level checked and confirmed at normal level. | 10.32 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0 |  |  | Generic description. RA needs to be amended appropriately by the user depending on overhauled items (whether pistons or bearings etc). This sample refers to main engine high pressure fuel injection pumps.
10.43 | Machinery items overhauled by S/Y have been confirmed as being in good working condition, i.e. pistons, bearings, stern tube, intermediate bearing, etc. | 10.32 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
11 | General Appearance and Condition | [9 empty] | 0 |  | 0 | [7 empty] | 0
11.1 | All heavy objects have been secured / Iashed for open sea passage. | 11.3 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
11.2 | Refrigerator chamber alarm and Hospital calling system tested I activated during sea trials. | 11.15 & 11.17 |  | DST | [6 empty] | 0 |  | 0 | [7 empty] | 0
11.3 | Confirmation that all tank vents are free and clear such as fuel, lube, water and sewage. | 11.7 |  | DDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
11.4 | Confirmation of properly painted load line, draft marks to be adequately visible. | 11.2 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
11.5 | Any gratings on deck are safely secured, including safe access to the bow. | 11.3 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
11.6 | Bottom plugs and rudder plug in place. | 2.9 & 11 |  | PDT | [6 empty] | 0 |  | 0 | [7 empty] | 0
| Item per category | VIQ #7 item No. | Completed by | Timing | Verified by | REMARKS | Criticality Exposure Index (CEI)
12 | Ice / sub-zero temperature Operations
12.1* | Use company SMS to verify precautions taken against sub zero temps/icing precautions and navigating in ice. Use of Form ….. (as appropriate) | 12.1 |  | PS
12.2* | PPE warm weather clothing checked, sufficient onboard | 12.6 12.7 |  | PS
12.3* | Engines e.g. L/B, rescue boat, emergency generator – anti freeze and low temp fuels used | 12.14 |  | PS
12.4* | Winter lubricants used in deck machinery | 12.6, 12.13, 12.17 |  | PS
12.5* | Heating systems to check for accommodation | 12.8 |  | PS
12.6* | Derricks/cranes checked | 12.17 |  | PS
12.7* | FO storage tank temps increased to appropriate levels | 12.2 |  | PS
12.8* | Sea chest steam injection/heating systems tested and fully operational | 12.5 |  | PS
12.9* | Adequate supplies of: sand, wooden mallets, snow scrapers, window scrapers, shovels, de-icing fluid | 12.9 |  | PS
12.10* | Canvas covers sufficient for tank valves, pv and vent mast riser, | 12.19 |  | PS
12.11* | Ballast water bubbling/heating system checked | 12.18 |  | PS
12.12* | Cargo tank heating coils/deck heaters checked operational | 12.19 |  | PS
12.13* | Tank cleaning heater drained | 12.17 |  | PS
12.14* | Heating for hydraulic system verified e.g. framo | 12.6, 12.17 |  | PS
12.15* | Sprinkler systems drained of water | 12.15 |  | PS
12.16* | FFE operational checks for cold weather as per SMS | 12.15 |  | PS