## RA DD CL
APPENDIX | [10 empty] | Code:
Issue No.:
Dry - Docking R.A. - AS AN EXAMPLE ONLY - Each company can use their own R.A. model | [10 empty] | Revision:
[11 empty] | Date: |  | 2019-12-01
| IDENTIFICATION OF HAZARD |  |  |  | ASSESSMENT OF RISK * |  |  |  | IMPLEMENTATION OF CONTROLS |  | FINAL RISK
No. | HAZARD |  | CAUSE | RESULT | (L1) Likelihood | (C) Consequence | (R) Risk (L1xC) | Risk Level | ACTION | REFERENCE DOCUMENT | (L2) Likelihood | (FR) Final Risk (L2xC) | Risk Level
2 | VESSEL'S DRYDOCKING | Certification & Documentation
2.1 |  | New Certificates / Test Records / Receipts issued during DD period not onboard. (VIQ. 2) | Humman error/ negligence. | Commercial implications in vessel's trading. | 2 | 1 | 2 | LOW | Verification prior sailing that all newly issued certificates are onboard, both by Master and attending superintendent. | Dry dock check list | 1 | 1 | LOW
2.2 |  | Certificates / Endorsements not correct (copies not sent to office ASAP). (VIQ. 2) | Humman error/ negligence. | Commercial implications in vessel's trading. | 2 | 1 | 2 | LOW | Verification prior sailing that all newly issued certificates are correct, both by Master and attending superintendent. | Dry dock check list | 1 | 1 | LOW
2.3 |  | VGP requirements breached / documentation not in order. Class Statement of Facts not prepared. (VIQ. 2) | Required inspections/ maintenance not carried out, reports for same not issued. Items overlooked/ forgoten. | Pollution/ Commercial implications in vessel's trading. | 2 | 2 | 4 | MEDIUM | Verification prior sailing that each VGP required form/ certificate/ statement have been issued in good order, both by Master and attending superintendent. All required inspections have been carried out to the satisfaction of the attending class surveyor. | -Dry dock check list -Biofouling Management Plan/ Records | 1 | 2 | LOW
2.4 |  | Class 'Factual Statement' that the Special Survey has been completed and that the ESP (Executive Hull Summary & Thickness Measurements) documentation is under preparation by Class head office (will be issued in due course) not issued. (VIQ.2) | Required inspections/ maintenance not carried out, reports for same not issued. Items overlooked/ forgoten. | Commercial implications in vessel's trading. | 2 | 1 | 2 | LOW | Verification prior sailing that relevant statement issued and final report is under preparation, both by Master and attending superintendent. | Dry dock check list | 1 | 1 | LOW
2.5 |  | Class factual statement for the pressure test of piping conducted not issued. (VIQ. 2, 8.3) | Leakage in way of piping. Report not issued, item overlooked/ forgoten. | Pollution hazards. Commercial implications in vessel's trading. | 2 | 2 | 4 | MEDIUM | Pressure test of piping performed during cargo tank washing operations prior docking; repairs (as/ if needed affected). Verification prior sailing that relevant statement issued, both by Master and attending superintendent. | Dry dock check list | 1 | 2 | LOW
2.6 |  | Class factual statement for the ETA structural support members. (VIQ. 2, 9.28) | Defect in way of underdeck supporting structure. Relevant inspections not carried out and/ or reports missing. | ETA equipment inoperative. Safety issues. Commercial implications in vessel's trading. | 2 | 3 | 6 | MEDIUM | Supporting structure is inspected by Class surveyor and attending superntendent. Verification prior sailing that relevant statement issued, both by Master and attending superintendent. | Dry dock check list Class checklist | 1 | 3 | LOW
2.7 |  | Vessel drawings, Fire/ Safety/ Emergency plans used during drydock period missing. Special tools, and other ship property not returned on board. (VIQ. 2) | Humman error/ negligence. | Safety hazards/ routine maintenance implications. | 3 | 3 | 9 | HIGH | Items landed/ handed over to the shipyard's personnel documented in relevant landing forms. Master/ Chief engineer frequently updated on aoutstanding items during daily safety meetings. Final check prior sailing is performed by ship's crew. | Landing forms/ onboard checklist | 1 | 3 | LOW
2.8 |  | QMS procedures for the Drydock have not been properly evidenced and records filed (inclusive of Risk assessment, Safety Committee Meeting records and Management of Change records). (VIQ. 2, 5.7) | Lack of familiarity with established procedures. | Safety hazards/ commercial implications. | 3 | 3 | 9 | HIGH | Verification prior dry-docking that all required QMS documentation has been submitted to the head office/ prepared by the head office (as applicable). Verification that all items/ inspections of the drydock checklist have been performed prior vessel's sailing. | Dry dock check list QMS established procedures | 1 | 3 | LOW
2.9 |  | Upper deck – accommodation and out-fittings damaged by shipyard. (VIQ. 2.15, 2.16) | Misconduct during shipyard assigned works. Improper inspection following completion of yard works. | Defective equipment not repaired in time for vessel's sailing. | 2 | 3 | 6 | MEDIUM | Daily progress meetings conducted during docking period. Repair specification and sailing Gantt constantly updated. Safety inspection is conducted on a daily basis by shipyard personnel and ship's safety officer. All defects are promptly identified and repaired prior vessel's departure. | Dry dock checklist QMS, PMS maintenance instructions | 1 | 3 | LOW
2.1 |  | Person trapped inside tank. Tank vents and sounding pipes obstructed. (VIQ. 2.9) | Lack of compliance with established procedures for man entry. Tank safety arrangements not operational. | Human injury/ casualty. Safety hazards. | 3 | 3 | 9 | HIGH | Procedures for entry into enclosed space are strictly followed. Entry into enclosed space during docking is prohibited without relevant entry permit from yard safety officer. Tank vents and sounding pipes are checked for unobstructed operation/ status. | Dry dock check list PMS maintenance instructions | 1 | 3 | LOW
2.11 |  | Cargo/ ballast hatch covers not structurally intact and water tight. (VIQ. 8.18) | Gaskets defective. Covers deformed. | Gas leakage on deck. Cargo/ water leakage on deck. | 2 | 3 | 6 | MEDIUM | Cargo hatches inspected/ repaired (as needed) during docking period. Replacement of rubber gasket is performed as required. Covers tightness tested on completion of repairs. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
2.12 |  | M/E L.O. sump tank manhole gaskets inside cofferdam leaking. (VIQ. 2.9) | Improper tightening/ defective gaskets. | Leakage of M/E lub oil. Potential ignition. Low sump tank level. Safety issues for personnel entering the cofferdam space. | 3 | 3 | 9 | HIGH | Sump tank cofferdam is inspected during docking period to confirm tightness of inspection manholes. Sump tank level is checked prior vessel's departure drydock. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
2.13 |  | Tanks and voids not free and clear of debris. (VIQ. 2.9) | Improper protection of openings during docking works. | Safety hazards for personnel entering the space. | 3 | 3 | 9 | HIGH | All space openings secured closed. Protection canvas is used as applicable in order to reduce amount of debris entering the space. Enclosed space entry permits issued as applicable. |  | 1 | 3 | LOW
2.14 |  | Agent unaware of the departure date/timings. (VIQ. 2) | Information with respect to undocking not promptly communicated. | Commercial implications. Delay in vessel's unberthing schedule. | 3 | 1 | 3 | LOW | Local attending agent imformed by yard's representative/ SRM of vessel's departure date 2 days prior actual sailing. Frequent updates given on daily progress/ safety meetings in order all paperwork to be promptly completed. Master reconfirms that all parties are aware and well informed of vessel's schedule. | QMS established procedures | 1 | 1 | LOW
3 |  | Crew Management
3.1 |  | Ship personnel are not adequately rested before departure. (VIQ. 3.2) | Intensive work load during docking period. | Safety hazards. | 3 | 3 | 9 | HIGH | Rest hours are monitored and diligently followed. No immediate sailing after completion of works (one day layby berth prior sailing allowed). | Rest hours log | 1 | 3 | LOW
3.2 |  | Not all crew on board prior to departure. (VIQ. 3.1) | Improper planning. Human error/ negligence. | Minimum safe manning not met.Safety hazards/ commercial implications. | 2 | 3 | 6 | MEDIUM | Crew shore leave ends 24hr prior vessel's sailing. Master confirms that all crew is onboard prior sailing. Master's permission for shore leave is requested. Crew shore passes at Master's control. | Deck log book | 1 | 3 | LOW
4 |  | Navigation and Communication
4.1 |  | ‘Preparation for departure’ tests and checks prior departure not carried out (VIQ. 4.3, 4.7) | Lack of familiarity with established procedures. Improper implementation of established procedures. | Safety hazards. | 3 | 3 | 9 | HIGH | Dedicated QMS checklist compiled and relevant checks performed to the satisfaction of OOW and Master. | Bridge-09 checklist ECR Preparation for Sea Checklist | 1 | 3 | LOW
4.2 |  | Navigation / Communication/intercom equipment (inclusive of emergency devices) / instruments operation test not carried out (Radars/ ARPA, Gyro Compasses, ECDIS, Steering gear/ Auto pilot, GMDSS/ Batteries, EPIRB/ SARTs) (VIQ. 4.7) | Defective equipment. Insufficient maintenance. | Navigational and safety hazards. | 3 | 3 | 9 | HIGH | Navigational equipment test prior vessel's sailing and during sea trial run. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
4.3 |  | Dead man alarm system, Navigation Bridge alarm system not tested / activated. (VIQ. 4.7) | Defective equipment. Insufficient maintenance. | Safety hazards. | 4 | 3 | 12 | HIGH | Equipment test prior vessel's sailing and during sea trial run. | Dry dock checklist ECR UMS Checklist | 1 | 3 | LOW
4.4 |  | Echo sounder and Doppler transducers not functioning correctly. (VIQ. 4.7) | Defective equipment. Insufficient maintenance.. | Safety / operational implications. | 4 | 3 | 12 | HIGH | Equipment serviced by Maker's authorized service engineer and tested prior vessel's sailing, during stay at the yard's layby berth. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
4.5 |  | Navigational equipment not tested prior departure. (VIQ. 4.7) | Defective equipment. Insufficient maintenance. | Navigational and safety hazards. | 4 | 3 | 12 | HIGH | Equipment serviced by Maker's authorized service engineer and tested prior vessel's sailing, during stay at the yard's layby berth. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
4.6 |  | Temporary notices, Navtex, weather information not received and passage plan not prepared. ECDIS pre-departure check list “Bridge-24” not completed. (VIQ. 4.13,4.17,4.20) | Established procedures not followed. Defect in relevant equipment. | Navigational and safety hazards. | 3 | 3 | 9 | HIGH | Passage plan prepared in line with company's procedures. Notices are updated in line with company's procedures. ECDIS test carried out and relevant documentation completed. | Dry dock checklist Bridge preparation for sea checklist ECDIS checklist | 1 | 3 | LOW
4.7 |  | Charts and publications, latest NTMS applicable for the intented voyage not available onboard. (VIQ. 4.12) | Established procedures not followed. | Navigational and safety hazards. | 3 | 3 | 9 | HIGH | All required publications and charts available onboard, confirmed by OOW and Master prior ship's sailing. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
4.8 | VESSEL'S DRYDOCKING | Navigational, security plan, Suez Canal search lights, not tested during dock trials. (VIQ. 4.20,7.4) | Improper maintenance/ lack of familiarity with established procedures. | Navigational and safety hazards. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the yard's layby berth. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
4.9 |  | Testing of general alarm, ship's whistles and gongs not performed. (VIQ. 4.7) | Defective equipment. Insufficient maintenance. | Vessel's audible warning system handicaped. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the yard's layby berth. | Dry dock checklist ECR UMS Checklist ECR Preparation for Sea Checklist | 1 | 3 | LOW
4.1 |  | Emergency power supply (batteries, UPS & chargers) not operational/ not tested. (VIQ 4.23, 10.36) | Batteries wasted. Charging equipment out of order. | No power supply to essential equipment, whilst main power supply interrupted. | 2 | 3 | 6 | MEDIUM | Verification by ship's electrician prior sailing that all emergency power supply equipment is operational under the presence of Class surveyor and attending superintendent. Charging equipment verified operational prior sailing. | Dry dock checklist QMS, PMS maintenance instructions | 1 | 3 | LOW
4.11 |  | Magnetic compass not adjusted. (VIQ. 4.7) | Drifting values with respect to magnetic north indication. | Navigational and safety hazards. | 3 | 3 | 9 | HIGH | Magnetic compass adjustment card issued during sea trials by a certified adjuster. | Dry dock check list PMS established procedures | 1 | 3 | LOW
5 |  | Safety Management
5.1 |  | Accommodation Ladders P & S and gangway operation/ load test not carried out and/ or Class statement/ certificate not issued (VIQ. 5.47) | Defective equipment. Defective braking arrangement. Worn wires. Damage in way of body. Insufficient maintenance. | Safety and commercial hazards. | 2 | 3 | 6 | MEDIUM | Load test carried out as part of the special survey during docking. Relevant documentation sighted/ checked by Master/ attending superintendent. | Class checklist Dry dock checklist | 1 | 3 | LOW
5.2 |  | L/boats (P & S) load test not carried out, units not rigged onboard/ not inspected with respect portable to equipment completness. (VIQ. 5.27, 5.28, 5.29 & 5.30) | Hooks and releasing equipment in poor condition. Missing inventory items. Units remain at yard's workshop. | Insufficient means to support life in an emergency situation/ incident. | 2 | 3 | 6 | MEDIUM | Equipment test as part of Class survey cycle. Tests verified by Class, shipyard and attending superintendent. Boats rigged and inspected onboard prior issuance of statutory certificates. Units' serviced by Maker's authorized service engineer. | Class checklist Dry dock checklist PMS instructions for the job | 1 | 3 | LOW
5.3 |  | Liferafts not properly stowed and auto release device not functioning correctly. Lashing not adequate. (VIQ. 5.28) | Careless installation by crew. Use of defective hydrostatic release. Impproper installation of the HRU. | Insufficient means to support life in an emergency situation/ incident. | 2 | 3 | 6 | MEDIUM | Assembly of equipment (releasing mechanism) by competent crew members. Stowing under the supervision of Master and Chief Officer. Lashing in line with Maker's instructions. Final check prior vessel's sailing. | Dry dock checklist PMS instructions for the job Maker's instructions | 1 | 3 | LOW
5.4 |  | Llife saving equipment not in place and not ready for use. (VIQ. 5.44) | Serviced equipment not returned onboard. Inadequate service of equipment. | Insufficient means to support life in an emergency situation/ incident. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items returned onboard prior vessel's sailing from dock. All items checked with respect to operational status. All items correctly positioned in designated place and ready for use. | Dry dock checklist PMS maintenance instructions Maker's instructions Solas training manuals | 1 | 3 | LOW
5.5 |  | P/Room rescue winch not in place or adequately available. (VIQ 5.20) | Defective equipment. Insufficient maintenance. | Insufficient rescue means in a rescue from pump room incident. | 3 | 3 | 9 | HIGH | Equipment check prior sailing. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
5.6 |  | Firefighting equipment-accessories not re-stowed in place-boxes etc. (VIQ. 5.42) | Serviced equipment not returdned onboard. Inadequate service of equipment. | Crew unable to suppress fire onboard. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items returned onboard prior vessel's sailing from dock. All items checked with respect to operational status. All items correctly positioned in designated place and ready for use. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions Solas training manuals | 1 | 3 | LOW
5.7 |  | MOB units not in place. (VIQ. 5.31) | Serviced equipment not returned onboard. Inadequate service of equipment. | Insufficient rescue means in a Man overboard incident. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items returned onboard prior vessel's sailing from dock. All items checked with respect to operational status. All items correctly positioned in designated place and ready for use prior sailing. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions Solas training manuals | 1 | 3 | LOW
5.8 |  | CO2 system not connected and not ready for use. (VIQ. 5.40) | Defective equipment. Insufficient maintenance. | Crew unable to suppress fire onboard. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System verification readiness confirmed prior sailing. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions Solas training manuals | 1 | 3 | LOW
5.9 |  | Fire / Emergency Pumps not operational. Fire main pipes / valves not pressure tested. (VIQ. 5.38, 5.41) | Defective equipment. Insufficient maintenance. Leakage in the piping. | Crew unable to suppress fire onboard. | 2 | 3 | 6 | MEDIUM | Verification prior sailing that each pump is operational; pressure test of the lines conducted by yard and verified by the attending Class surveyor. | Dry dock check list PMS maintenance instructions Surveyor's checklist | 1 | 3 | LOW
5.1 |  | Fire-Gas-Smoke-Thermal Detection alarms and General Alarm not tested. (VIQ.5.39) | System breakdown. Individual sensors malfunctioning. | UMS impared. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System verification readiness confirmed. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
5.11 |  | Remote shut-off system for accommodation and engine room Fire doors / Flaps / Dampers not operational/ not tested. (VIQ 5.45) | Interlock with fire detection system inoperative/ local releasing units defective. | Isolation/ suppression of fire impaired. | 2 | 3 | 6 | MEDIUM | System check prior/ during docking. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
5.12 |  | Pump room / accommodation / bosun’s store room gas monitoring systems not tested. (VIQ.5.21 & 5.22) | Sensors defective. Sampling pipes clogged. | Gas leakage not detected. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System verification readiness confirmed. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
5.13 |  | Permanent fire extinguishing systems for E/RP/R Deck, Galley and Accommodation not ready to use (VIQ. 5.40) | Activation system defective. Sensors and automation defective. | Crew unable to suppress fire onboard. | 2 | 3 | 6 | MEDIUM | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System verification readiness confirmed. | Dry dock checklist QMS, PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
5.14 |  | Personnel Protective Equipment (PPE) not available for use (VIQ 5.5) | Lack of familiarity with established procedures. | Increased crew hazard exposure. | 3 | 3 | 9 | HIGH | Verification during dry-docking and prior sailing that adequate PPE is available onboard by the ship's safety officer. Daily safety inspection during docking and safety meeting in order to ensure compliance with safety regulations. | Dry dock check list QMS established procedures | 1 | 3 | LOW
5.15 |  | Gas monitoring system defective/ inoperable. (VIQ. 8.46) | Sensors defective. Sampling pipes clogged. | Gas leakage not promptly identified. | 3 | 3 | 9 | HIGH | Equipment servicing and maintenance by Maker's authorized service engineer during docking. Re-commissioning and safety interlocks test performed prior ship's sailing. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
5.16 |  | All drills (as per Regulations) not executed prior to sailing. (VIQ. 5.12, 5.13) | Lack of familiarity with established procedures. Improper implementation of established procedures. | Crew unable to perform in a real emergency situation. | 3 | 3 | 9 | HIGH | Monitoring of Drills' requirements in line with relevant list. Required drill's performed during sea trials or prior vessel's sailing (as applicable). | Dry dock checklist Drills record book/ Bridge log book. | 1 | 3 | LOW
5.17 |  | Measurements taken and calibration certificates not received/ not in order(as applicable). (VIQ. 5.23) | Relevant inspections not carried out, reports for same not issued. Items overlooked/ forgoten. | Incorrect interpretation of readings. | 3 | 3 | 9 | HIGH | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System readiness confirmed. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
5.18 |  | Shipyard equipment has not been removed and delivered prior to departure. (VIQ. 5, 11.3) | Humman error/ negligence. | Loose equipment on deck posing injury hazard. Commercial implications. | 4 | 1 | 4 | MEDIUM | Ship repair manager and ship's crew check prior vessel's sailing to ensure that all items have been returned in line with list provided. | Dry dock checklist | 1 | 1 | LOW
5.19 |  | Shipyard personnel still onboard prior vessel's sailing. (VIQ. 5, 7.3) | Humman error/ negligence. | Safety / operational/ commercial implications. | 4 | 1 | 4 | MEDIUM | Updated departure list provided by Master. Vessel's clearance issued by harbour and security check is performed prior vessel's departure by immigration department. | Dry dock checklist | 1 | 1 | LOW
5.2 |  | Sprinkler or fire suppression systems not air tested to confirm free and clear. (VIQ. 5.40) | Piping clogged. | Crew unable to suppress fire onboard. | 3 | 3 | 9 | HIGH | Equipment serviced by Maker's authorized service engineer. All items checked with respect to operational status. System readiness confirmed. Class attended relevant tests/ checks as applicable. | Dry dock check list QMS established procedures Class checklist | 1 | 3 | LOW
5.21 |  | Pump Room safety systems not tested / not operational. (VIQ. 5.19, 5.35) | Improper maintenance of automation/ mechanical parts. Equipment defective. | Crew unable to suppress vapour escape/ contain leakage. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the layby berth in line with prescribed maintenance instructions. | Dry dock checklist Deck maintenance instructions | 1 | 3 | LOW
6 |  | Pollution Prevention
6.1 |  | Garbage delivery receipts (inclusive of oily slops) not supplied to Master. (VIQ 6.20) | Humman error/ negligence. | Pollution/ commercial hazards. | 3 | 2 | 6 | MEDIUM | Verification prior sailing that all required receipts are onboard, both by Master and attending superintendent. Garbage record book updated prior vessel's departure from drydock. | Dry dock checklist | 1 | 2 | LOW
6.2 | VESSEL'S DRYDOCKING | O/fill alarms, Shutdowns, and other steering alarms (E/Room, P/Room, Steering gear, Bosun's store space bilge alarms) not tested / not operational. (VIQ. 6.11) | Floaters defective. Triggering mechanisms inoperable. | Safety hazards/ pollution hazard. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the layby berth. Testing in the framework of renewal surveys. | Dry dock checklist PMS maintenance instructions ECR UMS Checklist | 1 | 3 | LOW
6.3 |  | Spectacle flange i.w.o cargo line overboard valve not turned (as applicable)/ valves not switched to closed position. ODME simulation test not performed. (VIQ. 6.4, 6.13) | Valves leaking. Improper maintenance/ lack of compliance with established procedures. | Pollution hazards. | 3 | 2 | 6 | MEDIUM | Discharge line blinded, associated valves secured closed and sealed with numbered tags. Relevant entry made in the oil record book. Entries and actual arrangement verified by Master and attending superintendent prior vessel's departure. ODM equipment calibrated by Maker's service engineer during docking period. | Dry dock checklist Maker's service report Maker's instructions | 1 | 2 | LOW
6.4 |  | Main Cool. S.W. & Fire P/ps Emergency Bilge Suction not closed. Seal no's (if applicable) not recorded to engine log book. (VIQ. 6.15) | Valves leaking. Improper maintenance/ lack of compliance with established procedures. | Suction loss/ air trapped in the sea water system. Bilge water discharged through SW overboard. | 3 | 3 | 9 | HIGH | Valves test as part of Class survey cycle. Tightness confirmed prior vessel's departure during dock and sea trials. Valves sealed with numbered tags and relevant entries made to the engine record book. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
6.5 |  | Oily Water Separator overboard valve open. Seal no. (if applicable) not recorded in Oil Record Book. Oily water separator not tested / calibrated. (VIQ. 6.17, 6.18) | Filters clogged/ automation defective. Overboard valve leaking. | Pollution hazard. | 3 | 2 | 6 | MEDIUM | Equipment test as part of Class survey cycle. Equipment calibrated by Maker's service engineer during docking period. Entries made to the engine record book and verified prior departure. | Dry dock checklist PMS instructions for the job Maker's instructions | 1 | 2 | LOW
6.6 |  | Systems / piping not flushed, as applicable. (VIQ. 6.4) | Foreign particles trapped in the piping. | Piping clogged/ filter clogging. Operational difficulties for machineries. | 3 | 3 | 9 | HIGH | Open up inspection of vessel's lines during drydocking. Cargo sea lines suitably blinded and status confirmed by Master/ Chief Officer during docking/ prior departure. | Dry dock checklist QMS, PMS maintenance instructions | 1 | 3 | LOW
6.7 |  | Contingency plan in case of failure: Emergency Plan & Training Manual – Pollution not in place. (VIQ. 6.1) | Procedures not established. | Safety and Pollution hazard. | 2 | 2 | 4 | MEDIUM | Relevant plan confirmed in place as per Company's instructions prior vessel's departure. Plan approved by the administration. | QMS iinstructions | 1 | 2 | LOW
6.8 |  | Means for managing spills not in place (continuous coaming, scupper plugs and spills kits). (VIQ. 6.2, 6.3) | Defective/ missing scupper plugs. Insufficient material for spill contamination. | Pollution hazard. | 4 | 3 | 12 | HIGH | Proper maintenance of associated equipment. Items checked as per PMS instructions prior vessel's departure from drydock. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
7 |  | Maritime security
7.1 |  | Security inspection not carried-out and no entry made in bridge logbook. (VIQ. 7.3) | Improper planning. Human error/ negligence. Lack of familiarity with established procedures. | Unidentified personnel remaining onboard. | 2 | 3 | 6 | MEDIUM | Access to the vessel during docking controlled by yard, implementing strict security measures. Security measures onboard continuously implemented by crew as per company's policy. Final security check performed prior vessel's sailing by ship's security officer. | Visitors book QMS procedures | 1 | 3 | LOW
7.2 |  | Cyber Security awareness/ policy not implemented onboard. Measures to prevent any breach not in place. (VIQ. 7.14-7.17) | Lack of familiarity with established procedures. Improper implementation of established procedures. | Safety hazards. | 3 | 3 | 9 | HIGH | Cyber security policy is promoted onboard through dedicated safety meetings. Safety committee meeting prior dry-docking and after completion of repairs performed. | Dry dock check list QMS established procedures | 1 | 3 | LOW
7.3 |  | I/T and O/T systems not secured after updates (VIQ. 7.15) | Lack of cyber security awareness. | Safety & Security hazard | 3 | 3 | 9 | HIGH | Procedures include the protection of IT/OT equipment from malware and virus attacks | Dry dock check list QMS established procedures | 1 | 3 | LOW
8 |  | Cargo and Ballast Systems - Petroleum
8.1 |  | Slop discharging piping leaking. (VIQ. 8.3, 8.62) | Impropper maintenance. | Safety hazards/ pollution hazard. | 2 | 3 | 6 | MEDIUM | Lines pressure test performed and relevant Class statement issued. | Dry dock checklist PMS maintenance instructions Class checklist | 1 | 3 | LOW
8.2 |  | MMC vapour locks damaged / leaking. (VIQ.8.12) | Improper maintenance/ external abuse. | Safety/ pollution hazard. | 2 | 3 | 6 | MEDIUM | Any defects on deck equipment is promptly identified and addressed during daily meetings. Rectification works completed prior vessel's departure. Tightness is confirmed during post dock cot inerting. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.3 |  | COW machines not operational. (VIQ. 8.34) | Defective gear box. Leaking piping. Stuck neck bush. | Pollusion hazard. Commercial implications. | 4 | 2 | 8 | HIGH | Operational status of machinery is thoroughly checked/ verified during pre-docking cot washing. Upon completion of washing operations units are maintained and kept ready for next operation. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 2 | LOW
8.4 |  | Heating coils leaking. (VIQ. 8.15) | Corrosion in way of penetration piece. Defect in way of piping. | Safety hazard. Commercial implications. | 4 | 3 | 12 | HIGH | Regular pressure testing of heating coils performed. Relevant records retained. Visual inspection of piping in way of cargo tanks performed during cargo tanks' inspections. | PMS maintenance instructions | 1 | 3 | LOW
8.5 |  | Cargo valves inoperative. Timing out of Maker's limits. (VIQ. 8.11) | Defective actuators. Defective solenoid valves/ directional flowmeters out of order. | Implications during cargo operations. Cargo commingling. Cargo shifting. | 4 | 2 | 8 | HIGH | Equipment tested/ maintained in accordance with Maker's and PMS instructions. Operation/ Timing check is conducted during drydock, concurrently with cot and wbt inspections. Valves tested during post dock trials. Relevant records kept in PMS. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 2 | LOW
8.6 |  | P/V valves not operational/ leaking. P/V breaker level incorrect. (VIQ. 8.21, 8.28) | Corossion/ fouling in way of lifting mechanism. Pitting in way of seat/ cone. Pressure adjustment incorrect. Breaker level incorrect. | Pressure rise in cargo tanks. Leakage of cargo vapour. O2 ingress. | 3 | 3 | 9 | HIGH | Manual activation (free movement confirmation), cleaning of the seat/ pressure cone performed during docking. Adjustment made with the use of test rig) to confirm tightness. Condition of valves/ seats checked during cot gas free state. Tightness confirmed during post drydocking inerting/ during sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.7 |  | C.O.Ps-W.B. Pumps, AUS malfunctioning. Emergency trip not operational. (VIQ. 8.8, 8.10) | Automation not calibrated/ adjusted. Leakage in way of mechanical seals. Defect in way of impeller/ casing. | Vessel unable to conduct cargo operations/ safety impaired. Cargo leakage in way of pump room. | 3 | 3 | 9 | HIGH | Cargo, ballast pumps and associated equipment is tested during discharging operations as well as during deslopping operations prior docking. Safety equipment is tested and verified operational. Systems maintained in line with PMS instructions. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.8 |  | IG system inoperative. (VIQ. 8.22 to 8.26) | Boilers breakdown, piping leakage, instrumentation failure, fans malfunction. Insufficient maintenance and lack of compliance with established maintenance program. | Vessel unable to maintain as safe cargo atmosphere with O2 level below 5%. | 3 | 3 | 9 | HIGH | Operation of IG system is checked during tank washing, prior docking. Maker's service engineer attending during docking for the 5 year maintenance of the boilers (inclusive of operational/ commissioning tests). Fans integrity is checked during docking period. Piping and instrumentation integrity is confirmed during trial inerting, prior ships sailing. | Dry dock check list PMS established procedures Maker's instructions | 1 | 3 | LOW
8.9 |  | CCR pressure and level sensors (COT and WBT) inoperative/ non calibrated. (VIQ. 8.19, 8.24, 8.25, 8.26) | Automation not calibrated/ adjusted. Defective transmitters. Instumentation defect. | Inaccurate/ misleading information during cargo operations. | 3 | 3 | 9 | HIGH | Zero calibration performed during docking whilst cot pressure and level is known (zero). Performance test for the pressure sensors performed during trial inerting prior sailing. | Dry dock checklist PMS established procedures | 1 | 3 | LOW
8.1 |  | Deck seal unit defective. S.W. supply pumps defective. Automation, safety trips and instrumentation malfunctioning. (VIQ. 8.27) | Internal defect of deck seal body. Insuffiicient maintenance of components. | IG system handicaped. | 3 | 3 | 9 | HIGH | Inspection of the inner deck seal body is performed during docking period. Performance test performed during trial inerting prior sailing. Automation and instrumentation verification during trial testing. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.11 |  | Oxygen analyser defective/ non calibrated. (VIQ. 8.26) | Measuring cell out of order. Calibration not performed with pure N2. | IG system handicaped. | 3 | 3 | 9 | HIGH | Units calibrated according to Maker's instructions and tested during trial inerting. Redundant unit fully operational/ calibrated. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.12 |  | Deck isolating local valves defective. Securing arrangements not in place/ operable. (VIQ. 8.20) | Corrosive environment. Insufficient maintenance of components. Defective pads. | Leakage of IG. Contamination of cargo. Vapour transfer through cot. | 3 | 3 | 9 | HIGH | All local isolating valves inspected tested during dry docking period. Relevant replacements/ repairs performed. Locking arrangements checked by vessel's crew prior vessel's sailing/ during sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.13 |  | Remote draft readings incorrect. (VIQ. 8.13) | Calibration not performed. Piping clogged due to hull fouling. Respective valves defective. | Misleading information transmitted to CCR. | 4 | 3 | 12 | HIGH | Inspection of valves performed as part of the Class survey. Piping integrity is checked both internally and externally. Calibration/ cross checking with draft marks performed whilst vessel at yard's layby berth. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.14 |  | P/V valves not operational/ leaking. P/V breaker level incorrect. (VIQ. 8.21, 8.28) | Corossion/ fouling in way of lifting mechanism. Pitting in way of seat/ cone. Pressure adjustment incorrect. Breaker level incorrect. | Pressure rise in cargo tanks. Leakage of cargo vapour. O2 ingress. | 3 | 3 | 9 | HIGH | Manual activation (free movement confirmation), cleaning of the seat/ pressure cone performed during docking. Adjustment made with the use of test rig) to confirm tightness. Condition of valves/ seats checked during cot gas free state. Tightness confirmed during post drydocking inerting/ during sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.15 |  | IG system inoperative. (VIQ. 8.22 to 8.26) | Boilers breakdown, piping leakage, instrumentation failure, fans malfunction. Insufficient maintenance and lack of compliance with established maintenance program. | Vessel unable to maintain as safe cargo atmosphere with O2 level below 5%. | 3 | 3 | 9 | HIGH | Operation of IG system is checked during tank washing, prior docking. Maker's service engineer attending during docking for the 5 year maintenance of the boilers (inclusive of operational/ commissioning tests). Fans integrity is checked during docking period. Piping and instrumentation integrity is confirmed during trial inerting, prior ships sailing. | Dry dock check list PMS established procedures Maker's instructions | 1 | 3 | LOW
8.16 |  | Gas monitoring system defective/ inoperable. (VIQ. 8.46) | Sensors defective. Sampling pipes clogged. | Gas leakage not promptly identified. | 3 | 3 | 9 | HIGH | Equipment servicing and maintenance by Maker's authorized service engineer during docking. Re-commissioning and safety interlocks test performed prior ship's sailing. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.17 |  | Manifolds not blanked. Drain valves not closed (VIQ. 8.41) | Flanges/ gasket damaged. Valves not isolating. Humman error/ negligence. | Pollution hazards. | 3 | 2 | 6 | MEDIUM | Manifold blanks and drain valves checked prior vessel's departure from dock. Tightness confirmed during cot washing operations. | Dry dock checklist | 1 | 2 | LOW
8.18 |  | Mast riser leakages. (VIQ. 8.19) | Defective isolating valve. | Loss of IG pressure. | 3 | 3 | 9 | HIGH | Tightness of valves confirmed prior vessel's docking. Cargo tightness test performed as per PMS instructions during trial inerting. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
8.19 |  | Cargo tanks High-level and overfill alarms not working properly. (VIQ. 8.14) | Defective alarm system | Pollution hazard; vessel unable to conduct cargo operations | 3 | 3 | 9 | HIGH | All cargo tanks High-level and overfill alarms tested during dry docking period. Relevant replacements/ repairs performed. All alarms checked by vessel's crew prior vessel's sailing and during sea trials. | Dry dock checklist PMS established procedures | 1 | 3 | LOW
8.2 |  | Pumproom leaking pipelines & valves. (VIQ. 8.44, 8.46, 8.47) | Leakage in way of valves and pipeline . | Vessel unable to conduct cargo operations/ safety impaired. Cargo leakage in way of pump room. | 3 | 3 | 9 | HIGH | Cargo, ballast pumps and associated equipment is tested and verified secure by crew. Safety equipment is tested and verified operational. | Dry dock checklist PMS established procedures | 1 | 3 | LOW
8.21 |  | Operational trial of the thrusters if available. (Where DP equipment available) | XXX | YYYY | ? | ? | ? |  | XXXX | YYYYY | ? | ? | ?
9 |  | Mooring
9.1 |  | Mooring machinery / windlasses – all cranes not tested. Hydraulic machinery not checked. (VIQ. 9.14,9.20, 8.50) | Increased wear in way of shaft bushes. Leakage in way of hydraulic system. Motor/ brake defect. | Mooring/ anchoring equipment handicaped. | 3 | 3 | 9 | HIGH | Lifting appliances test conducted as part of the Class survey cycle. All safety interlocks and shut downs verified operational. Mooring stations moving parts protected from dust/ sand blast during docking period. Function test of all mooring stations performed during undocking/ mooring along side yard's layby berth. Both anchor windlasses inspected, tested and brakes calibrated by shipyard during docking period in the presence of competent crew members and technical superintendent. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
9.2 |  | Mooring machinery / windlasses – all cranes not tested. Hydraulic machinery not checked. (VIQ. 9.14,9.20, 8.50) | Increased wear in way of shaft bushes. Leakage in way of hydraulic system. Motor/ brake defect. | Mooring/ anchoring equipment handicaped. | 3 | 3 | 9 | HIGH | Lifting appliances test conducted as part of the Class survey cycle. All safety interlocks and shut downs verified operational. Mooring stations moving parts protected from dust/ sand blast during docking period. Function test of all mooring stations performed during undocking/ mooring along side yard's layby berth. Both anchor windlasses inspected, tested and brakes calibrated by shipyard during docking period in the presence of competent crew members and technical superintendent. | Dry dock checklist Bridge preparation for sea checklist | 1 | 3 | LOW
9.3 |  | Ancor brakes loose/ stoppers not in position. (VIQ. 9.15) | Seizure of braking arrangement. Defective stoppers. Lack of compliance with established procedures. | Anchoring equipment handicaped. | 3 | 3 | 9 | HIGH | Windlass brake bands serviced/ renewed by shipyard personnel. On works completion brake test performed. Stoppers position confirmed prior vessel's departure for sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
9.4 |  | Changes to Mooring Equipment are not properly recorded (VIQ. 9.2, 9.3) | Humman error/ negligence. | Commercial implications. | 2 | 1 | 2 | LOW | Verification prior sailing that MSMP/LMP have been properly updated, both by Master and attending superintendent. | Dry dock check list | 1 | 1 | LOW
10 |  | Engine and Steering Compartments
10.1 |  | Engine Room alarm / monitoring and extension system not tested. (VIQ. 10.2, 10.4) | Defective equipment. Insufficient maintenance. | UMS system handicapped. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the shipyard's layby berth. | Dry dock checklist ECR UMS Checklist ECR Preparation for Sea Checklist | 1 | 3 | LOW
10.2 |  | Communications from control room, steering compartment and any other required location to bridge inoperative. (VIQ. 10.41) | Electronics defect. Poor wiring maintenance. | Crew unable to communicate with OOW during routine tasks as well as during emergency situation. | 3 | 3 | 9 | HIGH | Performance test whilst vessel at layby berth prior sailing as well as during post docking trials. | Dry dock checklist PMS instructions for the job Maker's instructions | 1 | 3 | LOW
10.3 |  | Srubber unit defective. Scrubber pump defective/ inoperable. (VIQ. 10.32) | Internal defect of scrubber body, demister and/ or gas inlet piece. Insufficient maintenance of components. | IG system handicaped. | 3 | 3 | 9 | HIGH | Inspection of the inner scrubber body is performed during docking period. Performance test performed during trial inerting prior sailing. Automation and instrumentation verification during trial testing. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.4 |  | Incinerator and safety devices not tested. (VIQ. 10.32) | Sensors/ automation defective. | Safety/ pollution hazard. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the layby berth. Testing in the framework of renewal surveys. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.5 |  | Engine room valves, remote shut-off and machinery shut-down system not tested. (VIQ. 10.17) | Interlocks not operational. Defective spring activated mechanisms. Pneumatic system clogging. | Machinery systems unable to be shut-off in an emergency situation. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing, during stay at the layby berth in line with prescribed maintenance instructions. Relevant check in the framework of Class survey. | Dry dock checklist PMS maintenance instructions Class checklist | 1 | 3 | LOW
10.6 |  | Engine Room Departure' ECR-07 tests and checks prior departure not performed. (VIQ. 10.32) | Lack of compliance with established procedures. | Safety hazards. | 3 | 3 | 9 | HIGH | Safety checks prior departure. Safety committee meetings onboard by Master and technical superintendents highlighting established procedures. | Dry dock checklist ECR Preparation for Sea Checklist | 1 | 3 | LOW
10.7 | VESSEL'S DRYDOCKING | Overhauled sea chests and valves are not operational / watertight. MGPS system not operational. (VIQ. 10.31) | Leakage in way of valves. Actuator defect. Automation malfunction. Anodes wasted. | Water ingress in E/R. Isolation not possible. Fouling in sw piping. | 3 | 3 | 9 | HIGH | Equipment test prior vessel's sailing by shipyard personnel; inspection and function test during stay at the yard's layby berth as well as during sea trials. | Dry dock checklist ECR Preparation for Sea Checklist | 1 | 3 | LOW
10.8 |  | Main switchboard and emergency switchboard automation test (incl. cleaning and bus bar securing bolt test) not performed. (VIQ. 10.23) | Defective contactors. Loose contacts in way of bus bars. | Electrical automation handicapped. Voltage regulation unstable. Electrical power loss. | 2 | 3 | 6 | MEDIUM | Performance test in the framework of class survey. Thermal imaging of all switchboards and panels prior vessel's entering drydocks. Rectification of outstanding deficiencies during docking period. Relevant reports issued by yard. | Class checklist Dry dock checklist Thermal imaging report | 1 | 3 | LOW
10.9 |  | Operational test, alarm & all trips of all generator engines not carried out. (VIQ. 10.32) | Defective pressure/ temperature transmitters. Overspeed device defective. | Damage to the generator. | 3 | 3 | 9 | HIGH | Performance test in the framework of class survey. Tests carried out whilst vessel at yard's layby berth prior sailing and during post docking trials. | Dry dock checklist PMS instructions for the job Maker's instructions | 1 | 3 | LOW
10.1 |  | Emergency generator operational test (using all available means), alarm & trips not carried out (incl. Confirmation of MGO filling). (VIQ. 10.16, 10.34) | Batteries wasted. Charging equipment out of order. Fuel starvation. | No power supply to essential equipment, whilst main power supply interrupted. | 3 | 3 | 9 | HIGH | Emergency generator is operated during entering/ exiting the drydock (auto start/ running under load). Safety trips and interlocks tested whilst vessel at yard's layby berth prior sailing. MGO tank level is checked prior vessel's departure for trials. | Dry dock checklist PMS instructions for the job Maker's instructions | 1 | 3 | LOW
10.11 |  | M/E turning gear interlock function not tested. (VIQ. 10.32) | Defective solenoid valve. | Damage of the turning gear motor/ gear. Engine slow turn not possible. | 2 | 3 | 6 | MEDIUM | Equipment (M/E automation and interlocks) serviced by Maker's authorized service engineer as per 5 year workscope. Relevant inspection reports issued. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
10.12 |  | Main Engine alarm and trip system check not carried out. (VIQ 10.32) | AMS system inoperative. Pressure and temperature transmitters defective. | Damage to the main engine. | 3 | 3 | 9 | HIGH | Equipment (M/E automation and interlocks) serviced by Maker's authorized service engineer as per 5 year workscope. Relevant inspection reports issued. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
10.13 |  | ME crankcase and scavenging spaces not inspected, possible defect in equipment not promptly identified. Aux blowers not tested. (VIQ.10.32) | Defective bearing. Broken piston ring. Worn liner. Leakage in way of blowers' seal. | Damage to the main engine. | 3 | 3 | 9 | HIGH | Relevant inspections carried out be Chief Engineer and attending technical superintendent. Deflection prior and after docking taken and measurements analysed. Blowers test run performed during layby berth stay and trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.14 |  | ME emergency and remote control operation not tested. (VIQ. 10.33) | System's communication failure. Local automation defective. | Main engine cannot be operated. | 3 | 3 | 9 | HIGH | Equipment (M/E automation and interlocks) serviced by Maker's authorized service engineer as per 5 year workscope. Relevant inspection reports issued. Engine test during yard's layby berth stay and sea trials from all available positions. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
10.15 |  | ME T/C oil level, prime pumps (as applicable) and safety / alarm settings not checked. (VIQ. 10.32) | Piping leakage/ clogging. Automation defective. | Damage to the Main engine T/C bearings. | 2 | 3 | 6 | MEDIUM | Units (M/E T/C) serviced by Maker's authorized service engineer as per 5 year workscope. Oil admission and automation is checked. Relevant inspection reports issued. Engine test during yard's layby berth stay and sea trials. | Dry dock checklist QMS, PMS maintenance instructions | 1 | 3 | LOW
10.16 |  | Aux. boiler(s) operational test, alarm & trips tests, safety devices and relief valves tests not carried out. (VIQ. 10.32) | Burner defective. Automation defective. Safety interlocks out of order. Safety valves stuck. | Steam plant handicapped. Operational safety impaired. | 3 | 3 | 9 | HIGH | Boiler safety, trip tests and structural inspection carried out in the framework of class survey. Maintenance and calibration of automation is performed by Maker's service engineer during docking. Boilers fire up performed in the presence of Makers service engineer during docking. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
10.17 |  | Exhaust gas boiler not internally inspected and pressure tested by pumps and safety relief valves not tested and calibrated. (VIQ.10.32) | Leakage in way of tubes. Increased fouling. Safety valves stuck. | Fire in the element. Water leakage. | 3 | 3 | 9 | HIGH | Boiler safety, trip tests and structural inspection carried out in the framework of class survey. Maintenance and calibration performed by crew during sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.18 |  | Rudder (all mode, including emergency steering) system operation test not carried out (VIQ. 10.16,10.39) | Auto pilots out of order. Transitters defective. Hydraulic equipment defective. | Rudder irresponsive. | 3 | 3 | 9 | HIGH | Rudder tests carried out during sea trials from all available positions (inclusive of emergency steering). Class verifies installation conforms with applicable regulations. | Class checklist Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.19 |  | No.1 and 2 steering gear power and control systems including auto change-over and failure alarms not carried out. Testing as per Solas not carried out (VIQ. 10.39,10.40,10.41) | Alarms and power transmission equipment out of order. Hydro oil leakage. Worn pumps. | Rudder irresponsive. | 3 | 3 | 9 | HIGH | Steering gear tests/ timing in line with Solas requirements carried out one day prior entering drydock. Auto operation/ change over, safety and trip interlocks tested during sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.2 |  | ME maneouvring system operational test from all stations carried out during sea trials (VIQ. 10.33) | System's communication failure. Local automation defective. | Main engine cannot be operated. | 3 | 3 | 9 | HIGH | Equipment (M/E automation and interlocks) serviced by Maker's authorized service engineer as per 5 year workscope. Relevant inspection reports issued. Engine test during yard's layby berth stay and sea trials from all available positions. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
11.21 |  | Aux. machinery auto change over procedure not tested. (VIQ. 10.32) | Pressure transmitters inoperative. | Automatic operation of stand by machinery inhibited. | 4 | 3 | 12 | HIGH | Equipment tested/ maintained in accordance with Maker's and PMS instructions. Auto change over tested during vessel's idle stay at layby berth. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.22 |  | Operational test of overhauled pumps not carried out. (VIQ. 10.32) | Wrong assembly of parts. Leakage in way of seals. | Pumps underperforming/ not operational. | 3 | 3 | 9 | HIGH | Each piece of equipment overhauled during docking tested on works completion. Relevant test reports issued. Test conducted in the presence of Chief Engineer. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.23 |  | Operational trial of the Stern Tube System not carried out. (VIQ. 10.32) | Insufficient lubrication in way of bush/shaft. Damage of the stern tube bush. | Loss of shelf propulsion. Oil leakage at sea. | 3 | 3 | 9 | HIGH | Inspection of the bush and shafting arrangements in the framework of Class survey. Replacement of seals by Maker's authorized service engineer. All works supervised by Maker's service engineer. Leak test carried out on completion of repairs. Operational test performed during post dock trials. Sufficient draft prior departure allowed (ballasting at layby berth) to avoid shaft vibrations, impact loads on shaft bush. | Dry dock checklist PMS maintenance instructions Maker's instructions Class checklist | 1 | 3 | LOW
10.24 |  | Air conditioning units not tested. (VIQ. 10.32) | Defect in compressors and/ or air handling units. | Vessel unable to maintain comfortable accommodation temperature. | 2 | 3 | 6 | MEDIUM | Both units operated during docking period. Relevant maintenance and inspections performed in line with PMS and Maker's instructions. Redundancy provided by 2 units installed. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.25 |  | Operational test of all miscellaneous systems that overhauled during D/D not carried out. (VIQ. 10.32 ) | Wrong assembly of parts. Spare parts of inferior quality used. | Safety/ pollution hazards. | 3 | 3 | 9 | HIGH | Works performed by yard/ crew during docking properly supervised. Overhauled machinery is tested on completion of repairs and relevant reports issued (in case of yard's works). Overhauled machinery tested during dock and sea trials. Authentic spare parts procured in time and used. | Dry dock checklist PMS established procedures | 1 | 3 | LOW
10.26 |  | ICCP system operation and indication check not performed. System not remained shut for fifteen (15) days after undocking. (VIQ. 10.32) | Insufficient corrosion protection. Incorrect reference readings, resulting in high/ low current output. Damage in way of freshly applied hull painting. | Hull coating condition deterioration. | 3 | 2 | 6 | MEDIUM | System check prior/ during docking performed by Maker's authorised service engineer. Maintenance requirements identified during pre-docking inspection. System trial test carried out during sea trials. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 2 | LOW
10.27 |  | All emergency lights in E/R, P/R, deck and accommodation space not tested / activated. (VIQ. 10.15, 11.9) | Cabling defect. Burnt light bulbs. | Poor/ insufficient illumination under emergency power supply. | 3 | 3 | 9 | HIGH | All emergency lights inspected during dock trials, prior vessel's departure. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.28 |  | Main engine bypass LO filter not inspected / cleaned. (VIQ. 10.32) | Foreign particles trapped in the filter. | Clogging of filter during operation. | 3 | 3 | 9 | HIGH | All filters inspected during docking interval and put in service during dock/ sea trials.Redundant filters in good order/ inspected. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.29 |  | Sea valves leaking. (VIQ. 10.31) | Defective or corroded seats/ valves. | Sea water ingress. Insufficient sealing of piping systems. | 4 | 3 | 12 | HIGH | Inspection of valves performed as part of the Class survey. Piping integrity is checked both internally and externally. Replacement valves having Class certificate installed. Lines and valves tested during dock trials. | Dry dock checklist PMS maintenance instructions Class checklist | 1 | 3 | LOW
10.3 |  | Machinery space bilge alarms not tested/ operational. (VIQ. 10.30) | Lack of compliance with established procedures. Floaters and associated parts in poor condition. | UMS system handicapped. Leakage in way of machinery spaces not promptly detected. | 3 | 3 | 9 | HIGH | All bilge alarms tested in the framework of Class survey. Associated equipment verified operational during dock trials. | Dry dock checklist Preparation for departure checklist Class checklist | 1 | 3 | LOW
10.31 | VESSEL'S DRYDOCKING | Scaffolding remaining in machinery spaces. Materials not properly secured for sea. (VIQ. 10.15) | Items forgotten by yard's personnel. Items used for docking works not properly secured. | Personnel injury during voyage. Damage to equipment due to sudden move of weights. | 4 | 3 | 12 | HIGH | All equipment used during docking is returned in designated position. Scaffolding removed from machinery spaces on yard's account; pending items discussed during daily safety meetings at the yard. | Dry dock checklist Daily safety meeting records | 1 | 3 | LOW
10.32 |  | Steam to HFO tanks closed/ HFO temperatures low. (VIQ 10.32) | Insufficient steam supply/ steam closed due to MGO drydock use. | Delay in vessel's sailing date. | 3 | 1 | 3 | LOW | Boilers fired up during dock trials. HFO system prepared prior vessel's departure drydock. Preheating activated to all required tanks. | Dry dock checklist | 1 | 1 | LOW
10.33 |  | Service/ settling tanks with excess sediments/ instrumentation and alarm system inoperative (VIQ.10.32) | Accumulated sediments due to prolonged use/ insufficient cleaning. Inspection for automation insufficiently performed. | Clogging of filter during operation. Fuel starvation. | 4 | 3 | 12 | HIGH | Both service settling tanks inspected and cleaned during docking. Internal space is inspected and all instrumentation/ alarm system is checked/ verified operational. On work's completion tanks are filled up and heated in order to be ready for sea trials. | Dry dock checklist PMS instructions for the job | 1 | 3 | LOW
10.34 |  | Fuel oil system (inclusive of pumps and filtering equipment) not operational. (VIQ. 10.32) | Change over to MGO not performed in line with dedicated procedure. Seizure of fuel pumps. Clogging of filters. | Propulsion loss, black out due to d/g fuel starvation. | 3 | 3 | 9 | HIGH | Equipment checked during docking trials. Redundant units confirmed operational. All filters checked/ cleaned prior departure yard's layby berth. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.35 |  | ME LO system (inclusive of pumps and filtering equipment) not operational. (VIQ. 10.32) | Seizure of pumps. Clogging of filters. | Propulsion loss. | 3 | 3 | 9 | HIGH | Equipment checked during docking trials. Redundant units confirmed operational. All filters checked/ cleaned prior departure yard's layby berth. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.36 |  | FW system not operational/ air trapted in the system. (VIQ. 10.32) | System not vented properly. Connections used during docking not properly re-instated. Pump seizure. | Loss of electrical power to insufficient cooling. Sea water contamination in the FW system. | 3 | 3 | 9 | HIGH | All shipyard connections removed prior vessel's departure. Piping/ coolers flushed with fresh water (in case of sea water use). Overhauled FW systems properly vented prior commissioning. Pumps test run. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.37 |  | SW water system not test run/ inoperative. (VIQ.10.32) | System not vented properly. Pump seizure. Filter clogging. | Propulsion loss, black out due to insufficient cooling. | 3 | 3 | 9 | HIGH | Filters cleaned during docking and boxed up prior vessel's departure. Units filled with water an pressure tested. Main sea water crossover line filled with water prior undocking and all sea chest filters vented once vessel on the water. Pumps test run performed. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.38 |  | Main air receivers insufficiently charged. Control air production and distribution malfunctioning. (VIQ. 10.32) | Damage of main air compressors/ control air compressor. Leakage in way of bottles and associated arrangements. | Vessel unable to start main engine. Pneumatic equipment inoperative. | 3 | 3 | 9 | HIGH | Bottles are pressurized and isolated from consumers whilst vessel at drydock. Pressure drop monitored and any leakages rectified. Main air compressors and control air compressor test run during dock trials/ sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.39 |  | Stern tube seals gravity tanks fwd and aft have not been connected. (VIQ. 10.32) | Insufficient lubrication in way of bush/shaft. Damage of the stern tube bush. Loss of shelf propulsion. Oil leakage at sea. | Propulsion loss. | 4 | 3 | 12 | HIGH | All works supervised by Maker's service engineer. Leak test carried out on completion of repairs. Operational test performed during post dock trials. | Dry dock checklist PMS maintenance instructions Maker's instructions | 1 | 3 | LOW
10.4 |  | Stern tube not full with lubrication oil/ gravity tank with insufficient oil quantity. (VIQ. 10.32) | Insufficient lubrication in way of bush/shaft. Damage of the stern tube bush. Loss of shelf propulsion. Oil leakage at sea. | Propulsion loss. | 3 | 3 | 9 | HIGH | All works supervised by Maker's service engineer. Leak test carried out on completion of repairs. Operational test performed during post dock trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.41 |  | Stern tube cooling water empty/ partialy filled. (VIQ. 10.32) | Hull structural defect. Leakage in way of manhole gasket | Insufficient cooling of the aft bush, insufficient oil film, damage of the bearing and shaft. Propulsion loss. | 3 | 3 | 9 | HIGH | Cooling water tank internally inspected during docking. On works completion tank is filled and pressure tested. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.42 |  | Insufficient oil in way of intermediate shaft bearing. (VIQ. 10.32) | Leakage in way of housing. Fresh charge not implemented. | Insufficient cooling of the intermediate bush/ insufficient oil film/ damage of the bearing and shaft. | 3 | 3 | 9 | HIGH | Oil level checked and proper lubrication confirmed during dock and sea trials. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
10.43 |  | Operational test of overhauled pumps not carried out. (VIQ. 10.32) | Wrong assembly of parts. Leakage in way of seals. | Pumps underperforming/ not operational. | 3 | 3 | 9 | HIGH | Each piece of equipment overhauled during docking tested on works completion. Relevant test reports issued. Test conducted in the presence of Chief Engineer. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
11 |  | General Appearance and Condition
11.1 |  | Heavy objects not secured / Iashed for open sea passage. (VIQ. 11.3) | Lack of safety awareness. | Safety hazards. | 2 | 3 | 6 | MEDIUM | Safety check prior departure drydock/ sailing. | Bridge preparation for sea checklist | 1 | 3 | LOW
11.2 |  | Refrigerator chamber alarm and Hospital calling system not tested/ activated during sea trials. (VIQ. 11.15, 11.17) | Defective sensors/ cabling/ automation. | Vessel unable to maintain sufficient temperature for refrigerating chambers. Vessel unable to preserve provisions. Hospitalized personnel unable to call assistance. | 3 | 3 | 9 | HIGH | Both units operated during docking period. Relevant maintenance and inspections performed in line with PMS and Maker's instructions. Redundancy provided by 2 units installed. Hospital alarm is tested during sea trials. | Dry dock check list PMS established procedures | 1 | 3 | LOW
11.3 |  | Tank vents (fuel, lube, water and sewage) not free. (VIQ. 11.7) | Cleaning/ inspection not performed. | Tank breathing arrangements not operational. | 3 | 3 | 9 | HIGH | All vent heads inspected during docking with respect to screen integrity/ cleanliness/ floaters integrity. Confirmatory inspection performed during dock trials, on completion of all deck works. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
11.4 |  | Load line marks not painted correctly. (VIQ. 11.2) | Improper instructions to yard's painting department. Improper application by shipyards' personnel. | Safety hazard. Commercial implications | 4 | 3 | 12 | HIGH | Marks verified by attending Class surveyor, relevant load line certificate issued (in case of multiple load line assignment). | Class Checklist/ certificate Dry dock checklist | 1 | 3 | LOW
11.5 |  | Safe access to bow obstructed, deck gratings not secured. (VIQ. 11.3) | Removed gratings not secured. Deck not cleared from foreign items/ obstacles. | Safety hazard. | 2 | 3 | 6 | MEDIUM | All gratings confirmed secured by crew prior departure yard's layby berth. Safe access to bow re-confirmed clear prior vessel's departure. | Dry dock checklist PMS maintenance instructions | 1 | 3 | LOW
11.6 |  | Bottom/ rudder plugs missing/ leaking. (VIQ. 2.9) | Improper installation, no pressure/vacuum test on completion of repairs. | Water ingress in way of tight compartments. | 3 | 3 | 9 | HIGH | Rudder plug vacuum test performed after plug installation. Bottom plugs not removed during docking as water drain is not required. Tightness checked during dock trials. | Dry dock checklist PMS established procedures | 1 | 3 | LOW
12 |  | Ice / sub-zero temperature Operations
12.1 |  | No precautions taken against sub zero temps/icing precautions and navigating in ice. (VIQ. 12.3)
12.2 |  | No sufficient PPE warm weather clothing on board. (VIQ. 12.6 & 12.7)
12.3 |  | No anti freeze and low temp fuels used in L/B, rescue boat, emergency generator engines. (VIQ. 12.14)
12.4 |  | No winter lubricants used in deck machinery. (VIQ. 12.6, 12.13 & 12.17)
12.5 |  | Heating systems for accommodation not checked. (VIQ. 12.8)
12.6 |  | Derricks/cranes not checked. (VIQ. 12.17)
12.7 |  | FO storage tank temps not increased to appropriate levels. (VIQ. 12.2)
12.8 |  | Sea chest steam injection/heating systems not tested. (VIQ. 12.5)
12.9 |  | No adequate supplies of: sand, wooden mallets, snow scrapers, window scrapers, shovels, de-icing fluid. (VIQ. 12.9)
12.1 |  | No sufficient canvas covers for tank valves, pv and vent mast riser. (VIQ. 12.19)
12.11 |  | Ballast water bubbling/heating system not checked. (VIQ. 12.18)
12.12 |  | Operation of cargo tank heating coils/deck heaters not checked. (VIQ. 12.19)
12.13 |  | Tank cleaning heater not drained. (VIQ. 12.17)
12.14 |  | Heating for hydraulic system not verified. (VIQ. 12.6 & 12.17)
12.15 |  | Sprinkler systems not drained of water. (VIQ. 12.15)
12.16 |  | FFE operational checks for cold weather not performed. (VIQ. 12.15)

## Risk Code
| Dry - Docking R.A. - AS AN EXAMPLE ONLY - Each company can use their own R.A. model |  |  |  | Code: | DD
[5 empty] | Issue No.: | 1
| Vessel's Drydocking - Risk Code |  |  |  | Revision: | 0
[5 empty] | Date: | 2019-12-01
RISK PRIORITY CODE
Risk (R) = Likelihood (L) x Consequence (C) |  |  |  | (C) CONSEQUENCE RATING
1-3: | LOW | Risk acceptable, can proceed with the task |  | 1 | 2 | 3
4-6: | MEDIUM | Task can be scheduled, however reviewing of controls recommended to reduce the risk rating |  | Commercial | Pollution | Safety
7-12: | HIGH | Cannot proceed with the task unless appropriate controls are taken to reduce the risk |  | Damage to asset or financial damage | Harm to the environment | Human injury, health damage or fatality
(L) LIKELIHOOD RATING | 1 | Very Unlikely | Never occurred in the industry | 1 | 2 | 3
| 2 | Unlikely | Occurred in the industry | 2 | 4 | 6
| 3 | Likely | Occurred more than once in the industry | 3 | 6 | 9
| 4 | Very Likely | Occurred more than once in the industry & at least once in the Company | 4 | 8 | 12